## Sheet1
Task | Owner | Year | Quarter | Required? | Length of Time | Notes
Phishing | Dom | 2018 | Q1 | Y | 1 Week | Active
Phishing | Dom | 2018 | Q1 | Y | 1 Week | Active | Team Members:
Phishing | Ryan | 2018 | Q1 | Y | 1 Week | Passive | Jason | Ryan
Phishing | Ryan | 2018 | Q2 | Y | 1 Week | Active | Alice | Dom
Phishing | Jason | 2018 | Q2 | Y | 1 Week | Passive
Phishing | Jason | 2018 | Q2 | Y | 1 Week | Passive
Phishing | Ryan | 2018 | Q3 | Y | 1 Week | Passive
Phishing | Ryan | 2018 | Q3 | Y | 1 Week | Active
Phishing | Alice | 2018 | Q3 | Y | 1 Week | Passive
Phishing | Alice | 2018 | Q4 | Y | 1 Week | Active
Phishing | Ryan | 2018 | Q4 | Y | 1 Week | Active
Phishing | Ryan | 2018 | Q4 | Y | 1 Week | Passive
External Perimeter Testing | Dom | 2018 | Q2 | Y | 4 Weeks | In-House
External Perimeter Testing | Dom | 2018 | Q3 | Y | 4 Weeks | Complaince Requirement
Active Directory | Alice | 2018 | Q4 | N | 2 Weeks | Can be moved to unknown assessment
Network Segmentation | Jason | 2018 | Q1 | Y | 2 Weeks | Can be moved to unknown assessment
Development Testing | Ryan | 2018 | Q1 | Y | 2 Weeks
Production Testing | Alice/Dom | 2018 | Q1 | Y | 3 Weeks
Production Testing | Jason/Alice | 2018 | Q4 | N | 3 Weeks | Can be moved to unknown assessment
Kubernetes Testing | Jason | 2018 | Q4 | Y | 3 Weeks | Required because of new service
- | - | - | - | - | - | -
Phishing | Ryan | 2019 | Q1 | Y | 1 Week | Passive
Phishing | Ryan | 2019 | Q1 | Y | 1 Week | Active
Phishing | Dom | 2019 | Q1 | Y | 1 Week | Active
Phishing | Dom | 2019 | Q2 | Y | 1 Week | Active
Phishing | Alice | 2019 | Q2 | Y | 1 Week | Passive
Phishing | Alice | 2019 | Q2 | Y | 1 Week | Passive
Phishing | Jason | 2019 | Q3 | Y | 1 Week | Active
Phishing | Jason | 2019 | Q3 | Y | 1 Week | Passive
Phishing | Ryan | 2019 | Q3 | Y | 1 Week | Active
Phishing | Ryan | 2019 | Q4 | Y | 1 Week | Active
Phishing | Dom | 2019 | Q4 | Y | 1 Week | Passive
Phishing | Dom | 2019 | Q4 | Y | 1 Week | Active
External Perimeter Testing | Jason | 2019 | Q2 | Y | 4 Weeks | In-House
Docker Testing | Alice | 2019 | Q3 | N | 2 Weeks | Can be moved to unknown assessment
Active Directory | Alice | 2019 | Q4 | N | 2 Weeks | Can be moved to unknown assessment
Network Segmentation | Jason | 2019 | Q1 | Y | 2 Weeks | Can be moved to unknown assessment
Development Testing | Dom | 2019 | Q1 | Y | 2 Weeks
Production Testing | Alice/Dom | 2019 | Q1 | Y | 3 Weeks
Production Testing | Ryan/Jason | 2019 | Q4 | N | 3 Weeks | Can be moved to unknown assessment
Kubernetes Testing | Ryan | 2019 | Q4 | Y | 3 Weeks | Required because of new service